## Gantt Chart
GANTT CHART for A1 & A2 | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Sunderland Project |  |  |  |  | COMPANY NAME | [6 empty] | OVO Marketing solution Limited
PROJECT MANAGER |  | Calvin, Ng Wai Ki |  |  |  |  | DATE | [6 empty] | 2020-05-11
DATASET |  | Bank Marketing Data Set (https://archive.ics.uci.edu/ml/datasets/Bank+Marketing)
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Assignment 1 ( 4 May - 13 Jun 2020 ) | [29 empty] | Assignment 2 ( 14 Jun - 17 Jul 2020) | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | 4 May - 8 May |  |  |  |  | 11 May - 15 May |  |  |  |  | 18 May - 22 May |  |  |  |  | 25 May - 29 May |  |  |  |  | 1 Jun -5 Jun |  |  |  |  | 8 Jun -12 Jun |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Assignment 1
1.1 | research for public dataset | Calvin | 2020-05-04 | 2020-05-12 | 8 | 100% | bar: 4 May - 8 May M to 11 May - 15 May T; 11 May - 15 May R to 11 May - 15 May F
1.1.1 | confirm topic and dataset | Calvin | 2020-05-12 | 2020-05-17 | 5 | 100% | bar: 11 May - 15 May T to 11 May - 15 May F
1.2 | Communication with Marta | Calvin, Marta | 2020-05-14 | 2020-05-17 | 3 | 60% | bar: 11 May - 15 May R to 18 May - 22 May M
1.3 | Analysis Dataset | Calvin | 2020-05-13 | 2020-05-25 | 12 | 50% | bar: 11 May - 15 May W to 25 May - 29 May M
1.4 | Research - Banking marketing Campiagn | Calvin | 2020-05-14 | 2020-05-26 | 12 | 60% | bar: 11 May - 15 May R to 25 May - 29 May T
2.4 | Idendifty the business problem | Calvin | 2020-05-14 | 2020-05-18 | 4 | 30% | bar: 11 May - 15 May R to 18 May - 22 May M
1.5 | Start to prepare Assignment 1 | Calvin | 2020-05-25 | 2020-06-12 | 17 | 10% | bar: 11 May - 15 May R to 11 May - 15 May F; 25 May - 29 May M to 8 Jun -12 Jun R
| Research for the Assignment | Calvin | 2020-05-29 | 2020-06-05 | 6 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F; 25 May - 29 May F to 1 Jun -5 Jun F
1.6 | Submit Assignment 1 | Calvin | 2020-06-12 | 2020-06-12 | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F; 8 Jun -12 Jun R
2 | Assignment 2 Planning
2.1 | Data Cleansing | Calvin | 2020-06-13 |  | 4 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F; WEEK 4 M to WEEK 4 R
2.2 | Data Manipulation | Calvin |  |  | 3 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F; WEEK 4 F to WEEK 5 F
2.3 | Confirm ML methods | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
2.4 |  |  |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
3 | Machine Learning Algorithm
3.1 | Prepare R code for ML | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
3.2 | Development Coding Plan | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
3.2.1 | Perform Coding | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
3.2.2 | Perform Testing | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
4 | Visualization and prepare Dashboard
4.1 | R Shiny | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
4.2 | Testing Web App | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
4.3 | Review with Marta | Calvin, Marta |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F
4.4 | Submit Assignment 2 | Calvin |  |  | 0 | 0% | bar: 11 May - 15 May R to 11 May - 15 May F